# ASSIN SOUTH DISTRICT ASSEMBLY

P. O. BOX 18, NSUAEM-KYEKYEWERE, VIA ASSIN DARMANG

CENTRAL REGION, GHANA

CS-0091-6994, southassin@gmail.com,http://assda.wordpress.com

0501173520

Our Ref: ASDA/A.3/VOL.6/2

Your Ref……………………….. 					           	4th November, 2025

SUBMISSION OF 2025 APPROVED ANNUAL ACTION PLAN

I do submit herewith 20225 Approved Annual Action Plan of Assin South District Assembly for your perusal.

Thank you.

# RICHARD ANSAH AMOAFO

# (DISTRICT COORDINATING DIRECTOR)

# For: DISTRICT CHIEF EXECUTIVE

# THE DIRECTOR GENERAL,

# NATIONAL DEVELOPMENT PLANNING COMMISSION

# ACCRA.

# Thr:

# THE REGIONAL MINISTER

# CEMTRAL REGIONAL COORDINATING COUNCIL

# CAPE COAST

Attn:

THE REGIONAL ECONOMIC PLANNING OFFICER

# CEMTRAL REGIONAL COORDINATING COUNCIL

# CAPE COAST

# Cc:

# All Assembly Members,

# Assin South D/Assembly

# Nsuaem/Kyekyewere

|  | ASSIN SOUTH DISTRICT ASSEMBLY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2025 ANNUAL ACTION PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | OBJECTIVE: To ensure efficient management and administration for effective service delivery. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NO | PROJECTS | LOCATION | TIMEFRA ME (2026) |  |  |  |  |  | COST |  |  |  |  |  |  |  |  |  |  | PROJECT STATUS |  |  |  |  | IMPLEMENTING INSTITUTION/DEPAR |  |  |
|  |  |  | Q 1 | Q 2 |  | Q 3 |  | Q 4 |  | GOG |  | DACF | IGF |  | DACFRFG |  | Other |  |  | Ne w | Ongo ing |  |  |  | Lead | Collaborating |  |
| 1 | Organization of various statutory meetings (General Assembly, Management, Sub-Committee, EXECO, DISEC and others) | District Assembly |  |  |  |  |  |  |  |  |  | 60,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | Dist. Asse | Stakeholders |  |
| 2 | Celebration of National and International Days (Emancipation, NAFAC, Independence, etc.) | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  | 20,000.00 |  |  |  | X |  |  |  | Dist. Assembl y | MOFA, GES, CNC, etc. |  |
| 3 | Provision of Office and Operational Logistics for Effective Service Delivery | District wide |  |  |  |  |  |  |  | 15,000.00 |  | 60,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembly | Procurement Unit |  |
| 4 | Maintain and Manage Assembly Assets and Fleet and Road Safety education | District wide |  |  |  |  |  |  |  |  |  | 94,911.36 |  |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembl | Transport Office |  |
| 5 | Provide logistical support to decentralized departments and substructures | District wide |  |  |  |  |  |  |  |  |  | 32,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembly | Procurement Unit |  |
| 6 | Strengthening Institutional Management and Administrative Support | District wide |  |  |  |  |  |  |  |  |  | 289,970.43 |  |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembl y | Administrative Unit |  |
|  | OBJECTIVE: To improve effective planning, budgeting, and coordination for sustainable development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Planning, Budgeting and Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Preparation of Strategic documents; MTDP, Composite budget, FFR, AAP, IAP, Annual Accounts, etc. | District wide |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | DPCU | Dist. Assembly |  |
| 8 | Participatory Monitoring and evaluation of projects and programmes | District wide |  |  |  |  |  |  |  |  |  | 70,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | DPCU | Dist. Assembly |  |
| 9 | Sensitization on Road Safety regulation | District wide |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | Transport Unit | Dist. Assembly |  |
| 10 | Update the District statistical database and district administrative data | District wide |  |  |  |  |  |  |  | 1,000.00 |  | 10,000.00 |  |  |  |  |  |  |  |  | X |  |  |  | Statistics Dept. | Dist. Assembly |  |
| 11 | Collection of data on businesses in 2 Area councils and signpost in the District | District wide Nyankumasi & Andoe |  |  |  |  |  |  |  |  | 1,500.00 |  |  | 3,000.0 0 |  |  |  |  |  |  |  | X |  |  | Statistics Dept. | Dist. Assembly |  |
| 12 | Contribution to counterpart funding of development projects and programmes | District wide |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | Stakeholders |  |
|  | OBJECTIVE: Deepen political and administrative decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Local Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Organize DCE’s community engagement and Town Hall Meetings | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | Dist. Assembl y | ISD, DPCU |  |
|  | OBJECTIVE: To strengthen the skills and knowledge of staff and Assembly members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | HUMAN RESOURCE DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Capacity building and orientation of Staff, NSS personnel and Assembly members (Client service and performance management) | District wide |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | HR | Consultants |  |
|  | OBJECTIVE: Improve Quality Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Education Quality and Access Improvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | Enhance Educational Support and Performance Improvement | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  | GES | Dist. Assembly |  |
| 16 | Procurement of School desks (684 dual, 478 Mono, 110 hexagonal desks) and 200no. Tables & chairs for teachers | Selected Schools |  |  |  |  |  |  |  |  |  | 173,763.58 |  |  | 100,000. 00 |  |  |  |  |  |  | X |  |  | Dist. Assembl y | GES |  |
| 17 | Organize my first day at school | District wide |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 18 | Capacity building workshop for all basic school teachers and organize refresher course and week celebration for all KG teachers | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 19 | Conduct annual school census in all basic and second cycle schools | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 20 | Sponsorships and bursaries for needy but brilliant students | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 21 | Support to Ghana School Feeding Programme | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 22 | Orientation workshop for newly posted teachers | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 23 | Organize national standardized assessment test (NSAT) for class 2 & 4 | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  | GES |  | Dist. Assembly |  |
| 24 | Construction of 1No. 6-Unit Primary Classroom Block with office and store | Ongwa |  |  |  |  |  |  |  |  |  | 1,111,970. 23 |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembly |  | GES |  |
| 25 | Construction of 1No. 2-Unit KG Classroom Block with office and store | Adiembra,Tebil |  |  |  |  |  |  |  |  |  | 524,111.70 |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembly |  | GES |  |
| 26 | Construction of 1No. 3-Unit Primary Classroom Block with office and store | Baafikrom |  |  |  |  |  |  |  |  |  | 715,244.26 |  |  |  |  |  |  |  | X |  |  |  | Dist. Assembly |  | GES |  |
| 27 | Completion of classroom blocks | Ningo, Tutuda, Dadieso |  |  |  |  |  |  |  |  |  | 2,351,326. 19 |  |  |  |  |  |  |  |  |  | X |  | Dist. Assembl |  | GES |  |
| 28 | Completion of 5No. stalled classroom block projects and District Education Office | Damtekrom, Dawumako Ampenkro, Tomfokro, Nsuaem, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,000,000. 00 |  |  | X |  | GETFU ND |  | MoE |  |
| 29 | Renovation of classroom blocks | District wide |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  |  |  |  | 800,000.00 |  | X |  |  | Dist. Assembl y |  |  | GES/Donor Partners |  |
| 30 | Construction of Astro turf pitches | Amanso and Kruwa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MP |  | Dist. Assembly |  |
| 31 | Construction of 1No. 3-unit teachers quarters and community education centre (ICT Centre) | Ongwa Area Council |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,000,000. 00 | X |  |  |  | MP/MoE /GIFEC |  | Dist. Assembly |  |
| 32 | Renovate and Operationalize existing community education centre (ICT Centre) at Nsuaem | Nsuaem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 350,000.00 |  |  |  |  | MP/MoE /GIFEC |  | Dist. Assembly |  |
|  | OBJECTIVE: Improve access to quality healthcare delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Health Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33 | Support to Ghana Health Service Activities | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | GHS | Dist. Assembly |  |
| 34 | Support to MSHARP, HIV/AIDS activities | District wide |  |  |  |  |  |  |  |  |  | 93,688.18 |  |  |  |  |  |  |  |  |  | X |  |  | GHS | Dist. Assembly |  |
| 35 | Provision of incentives to staff in deprived areas and sponsorship of at least one hardworking CHO to enrol in midwifery | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | 20,000.00 |  |  |  |  |  | X |  |  | GHS | Dist. Assembly |  |
| 36 | Support to malaria control programmes and disease control activities | District wide |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | GHS | Dist. Assembly |  |
| 37 | Completion of 2No. Community based Health and Planning Services (CHPS) and furnishing with CHPS items | Appiakrom Dominase |  |  |  |  |  |  |  |  |  | 1,612,225. 54 |  |  |  |  |  |  |  |  |  | X |  |  | Dist. Assembl y | GHS |  |
| 38 | Completion of 4no. CHPS Compound | Assin Kumasi, Nkubem Framase , Ochiso & Aseratoase |  |  |  |  |  |  |  |  | 1,671,927.78 | 491,180.03 |  |  |  | 573,648.00 |  |  |  |  |  | X |  |  | KAKUM HIA | Dist. Assembly GHS |  |
| 39 | Expansion of Health Centre | Ongwa, Manso |  |  |  |  |  |  |  |  |  |  |  |  |  | 578,765.45 |  |  |  | X |  |  |  |  | KAKUM HIA | Dist. Assembly GHS |  |
| 40 | Expansion and Renovation of health facilities | District wide |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  |  | 250,000.00 |  |  |  | x |  |  |  |  | Dist. Assemby | GHS |  |
| 41 | Extension of electricity to CHPS Facilities | Bankyease CHPS Nuanua Fante CHPS |  |  |  |  |  |  |  |  |  | 130,000.00 |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | GHS/ECG |  |
|  | OBJECTIVE: Enhance access to improved and sustainable environmental sanitation services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Water, Environmental Sanitation and Hygiene |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ENVIRONMENTAL HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 42 | Evacuate refuse dumps, maintaining and levelling of final disposal site | District wide |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 43 | Organize national sanitation day | District wide |  |  |  |  |  |  |  |  |  | 120,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 44 | Undertake district wide fumigation exercise | District wide |  |  |  |  |  |  |  |  |  | 160,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 45 | Monitor and supervise environmental service providers | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 46 | Conduct sensitization on WASH activities | District wide |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 47 | Support implementation of community led total sanitation | District wide |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 48 | Undertake desilting of public drains and gutters | District wide |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU NADMO | Dist. Assembly |  |
| 49 | Sensitization and training on school health hygiene for students, teachers and cooks in basic schools | District wide |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 50 | Conduct domicilary premises, hospitality premises and house inspection to ascertain the level of sanitation | District wide |  |  |  |  |  |  |  |  |  | 787,205.00 |  |  |  |  |  |  |  |  |  | X |  |  | EHSU | Dist. Assembly |  |
| 51 | Provision of two slaughter facilities (house) in Assin Andoe and Nyankomase Ahenkro Markets | Andoe Nyankumasi market |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,000,000. 00 |  |  |  | X |  |  |  |  | Dist. Assembl y | EHSU/Agric |  |
|  | WATER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 52 | Drilling and Construction of 5No. Mechanized Boreholes with Overhand tanks | Nkwanta, Domi and Others |  |  |  |  |  |  |  |  |  | 1,200,000. 00 |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | EHSU |  |
| 53 | Drilling and Construction of 5No. Handpumps | Selected Schools |  |  |  |  |  |  |  |  |  | 473,763.58 |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | EHSU |  |
| 54 | Repair and maintenance of 10 No. Boreholes | District wide |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | EHSU |  |
| 55 | Rehabilitate and operationalize the Adankwaman water project through household connection for consumption | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,000,000. 00 |  |  |  | x |  |  |  |  | CWSA | Dist. Assembly |  |
|  | OBJECTIVE: To strengthen disaster preparedness and risk reduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Disaster Management and Prevention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | NADMO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 56 | Public sensitization on disaster prevention and mitigation | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  | NADMO | Dist. Assembly |  |
| 57 | Procure relief items for disaster victims | District wide |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | NADMO | Dist. Assembly |  |
| 58 | Prepare disaster preparedness, risk and heat plans | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | NADMO | Dist. Assembly |  |
| 59 | Undertake emergency response | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | NADMO | Dist. Assembly |  |
|  | OBJECTIVE: Mitigate climate change impacts and enhance resilience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Climate Change and Green Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Climate Change Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 60 | Conduct Climate Change awareness and sensitization programmes in line with the GCFRP | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  |  |  | X |  |  | DPCU | Dist. Assembly |  |
| 61 | Conduct Fire Education in all 10 CREMAs | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  | X |  |  | DPCU | Dist. Assembly |  |
| 62 | Conduct Forest Monitoring to ensure compliance with REDD+ Strategy | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 18,000.00 |  |  |  |  |  | X |  |  | DPCU | Dist. Assembly |  |
| 63 | Undertake national tree for life planting exercise | District wide |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  | 5,000.00 |  |  |  |  |  | X |  |  | NADMO | Dist. Assembly |  |
|  | OBJECTIVE: Strengthen social protection for the vulnerable and excluded |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Social Protection and Poverty Reduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Social Welfare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 64 | Supervision and Impact Assessment of LEAP Payments to Households and Case Management | 66 LEAP communities |  |  |  |  |  |  |  |  | 2,000.00 | 3,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 65 | Capacity building and Skills training for 80 PWDs | District wide |  |  |  |  |  |  |  |  | 3,000.00 | 3,000.00 |  | 4,000.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 66 | Distribution of Modalities aids to 200 PWDs | District wide |  |  |  |  |  |  |  |  | 3,000.00 | 4,000.00 |  | 1,600.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 67 | Conduct Social Investigations & enquiries | District wide |  |  |  |  |  |  |  |  | 1,000.00 | 1,000.00 |  | 600.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 68 | Monitoring and Registration of Day-Care Centres (ECDC), NGOs & ECDC Care givers & Supervisrors training | District wide |  |  |  |  |  |  |  |  | 2,000.00 | 1,000.00 |  | 1,500.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 69 | NHIS Indigene Registration and Renewal for 1000 No. vulnerable persons | District wide |  |  |  |  |  |  |  |  | 4,000.00 | 8,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | DSW | Dist. Assembly |  |
| 70 | After care services, Case management, follow-ups, family tracing & SWIMS Reporting | District wide |  |  |  |  |  |  |  |  | 3,000.00 | 1,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  | DSW |  | Dist. Assembly |
|  | Integrated Social Services (ISS) Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 71 | Sensitization on Gender Based Violence Prevention & Response in 10 schools & 5 communities | Specific communities & schools |  |  |  |  |  |  |  |  | 3,000.00 | 3,000.00 |  | 1,000.00 |  |  |  |  | 5,000.00 |  |  | X |  | DSW |  | Dist. Assembly |
| 72 | Social Education on Social Issues in 10 No. schools & communities | District wide |  |  |  |  |  |  |  |  | 2,500.00 | 3,000.00 |  | 2,000.00 |  |  |  |  | 4,000.00 |  |  | X |  | DSW |  | Dist. Assembly |
| 73 | ISS Stakeholder Review Meetings, Strengthening Referrals & Linkages | District wide |  |  |  |  |  |  |  |  | 1,000.00 | 1,000.00 |  | 2,000.00 |  |  |  |  | 2,000.00 |  |  | X |  | DSW |  | Dist. Assembly |
|  | Child Labour Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 74 | Sensitisation of 20 communities on Child Labour, Forced Labour using behavioural change techniques | Specific communities |  |  |  |  |  |  |  |  |  | 2,000.00 |  | 4,000.00 |  |  |  |  | 30,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 75 | Undertake Continuous training of District Child Protection Committee members to better coordinate child labor related interventions | Dist. Assembly Conference room |  |  |  |  |  |  |  |  |  | 2,000.00 |  | 2,000.00 |  |  |  |  | 3,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 76 | Train members of the Social Services Sub-Committee to support coordination and implementation of child labor activities in communities | Dist. Assembly Conference room |  |  |  |  |  |  |  |  |  | 2,000.00 |  | 2,000.00 |  |  |  |  | 3,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 77 | Training of 100 CCPC members on Child protection related issues | Dist. Wide |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 10,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 78 | Monthly Radio sensitization on child protection in the District | Nyankumasi Ahenkro (Bohyeba fm) |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 1,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 79 | Training of 10 SISOs on Child labour related activities | 10 Circuits |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 2,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 80 | Support 10 School Management Committees (SMCs) and PTAs to monitor and report child labor acts | Specific schools |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 2,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 81 | Establish child protection clubs in 5 schools as structures for advocacy | Specific schools |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 5,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 82 | Organize training for HODs/Management to provide conscious support to social services | Dist. Assembly Conference room |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 2,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 83 | Provide comprehensive child protection remediation support including psychosocial counselling | DSW office |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 1,000.00 |  |  | X |  | DCPC |  | Dist. Assembly |
| 84 | Ensure vulnerable populations benefit from various social protection services and safety net programmes | Dist. Wide |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  | 1,000.00 | X |  |  |  | DCPC |  | Dist. Assembly |
|  | Community Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 85 | Support to Gender mainstreaming activities & VSLAs | Dist. Wide |  |  |  |  |  |  |  |  | 2,000.00 | 2,000.00 |  | 1,000.0 0 |  | 4,000.00 |  |  |  |  |  | X |  |  | Gender Desk Office | Dist. Assembly |  |
| 86 | Increase Participation of women in governance and decision making at the local level through orientation and training | Dist. Wide |  |  |  |  |  |  |  |  |  | 2,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Gender Desk Office | Dist. Assembly |  |
| 87 | Extension services, vocational training & self-help initiatives | Dist. Wide |  |  |  |  |  |  |  |  | 2,000.00 | 2,000.00 |  | 1,200.00 |  |  |  |  |  |  |  | X |  |  | Gender Desk Office | Dist. Assembly |  |
|  | OBJECTIVE: Promote local economic development through agriculture and job creation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Agriculture & Local Economic Development (LED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 88 | Technical Training of 25 Apprentices in Welding, Fabrication and Mechanical Engineering to promote local economic development (LED) | District wide |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  | 5,000.00 |  |  |  |  |  | X |  |  | RTF | Dist. Assembly |  |
| 89 | Apprenticeship to entrepreneurship training for 150 youth and 50PWDs | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  | X |  |  | BAC | Dist. Assembly |  |
| 90 | Agric and Agribusiness to entrepreneurship training for 200 youth and 50 PWDs | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  | X |  |  | BAC | Dist. Assembly |  |
| 91 | MSME business acceleration training for 50 women owned businesses | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  | X |  |  | BAC | Dist. Assembly |  |
| 92 | Business Counseling to promote Local economic development (LED) | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  | X |  |  | BAC | Dist. Assembly |  |
| 93 | Support Graduate Apprentice to acquire NVTI certificates | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  | X |  |  | RTF | BAC |  |
| 94 | Promotion of tourism development across the District and participation in Exhibitions | District wide |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | DPCU | Dist. Assembly |  |
| 95 | Collect and build database for development of tourist sites in the District | District wide |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | DPCU | Dist. Assembly |  |
| 96 | Operationalize the factory under 1D1F Progarmme | Kyekyewere |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  | Dist. Assembl y | REP, MoTA |
|  | OBJECTIVE: Enhance agricultural production and agri-business for economic transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Agricultural and Agribusiness Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | AGRICULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 97 | Enhance the adoption of improved technologies by small holder farmers and other organizations to increase yields of crops under Feed Ghana Programme | District wide |  |  |  |  |  |  |  |  |  | 61,840.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 98 | Improve livestock technologies to increase production of local poultry birds by 10% and small ruminants and pigs by 15% under Feed Ghana Programme | District wide |  |  |  |  |  |  |  |  |  | 6,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 99 | Reduce post-harvest losses along maize, rice and cassava by 15%, 20% and 30% respectively by 2026 | District wide |  |  |  |  |  |  |  |  |  | 6,400.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 100 | Improve adoption of improved technologies by men and women farmers by 25% by 2026 | District wide |  |  |  |  |  |  |  |  |  | 26,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 101 | Increase income from livestock rearing by men and women by 10% and 25% respectively by 2026 | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 102 | Develop 100 micro and 15 small scale irrigation schemes as well as agricultural management systems | District wide |  |  |  |  |  |  |  |  |  | 2,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
| 103 | Reduce stunting and overweight in children as well as Vit. A, iron and iodine deficiencies in children and women of reproductive age by 20% | District wide |  |  |  |  |  |  |  |  |  | 3,000.00 |  | 1,000.00 |  |  |  |  |  |  |  | X |  |  | Dept of Agric | Dist. Assembly |
|  | OBJECTIVE: To create sustainable jobs for Ghanaians. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: 24 Hour Economy Market & Accelerated Export Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 104 | Construction of Model Market Complex with Ancillary Facilities |  |  |  |  |  |  |  |  |  |  | 4,684,408. 96 |  |  |  |  |  |  |  |  |  |  |  |  | MoLGC RA | Dist. Assembly |
|  | OBJECTIVE: Expand infrastructure development for socio-economic growth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Infrastructure & Basic Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 105 | Construction of 10 No. Pipe culverts and Bridges | District wide |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  | 300,000. 00 |  |  |  |  | X |  |  |  |  | Works Dept. | Dist. Assembly |
| 106 | Rehabilitation and Spot improvement of 40km of District feeder roads | District wide |  |  |  |  |  |  |  |  |  | 300,000.00 |  |  |  |  |  |  |  | X |  |  |  |  | Works Dept. | Dist. Assembly |
| 107 | Enhance and expand rural telecommunication infrastructure and network coverage. | District wide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,000,000. 00 |  | x |  |  |  |  | GIFEC/T ELCOS | Dist. Assembly |
| 108 | Rural Electrification Extension Project | District wide |  |  |  |  |  |  |  |  |  | 1,000,000. 00 |  |  |  |  |  | 1,000,000. 00 |  | x |  |  |  |  | ECG, MoEGT | Dist. Assembly |
|  | OBJECTIVE: Promote sustainable spatially integrated development of human settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PROGRAMME: Spatial Planning & Human Settlement Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PHYSICAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 109 | Street naming and property numbering | District wide |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  | X |  |  |  |  | Physical Planning Dept. | Dist. Assembly |
| 110 | Preparation of 2 No. New spatial plans | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | Physical Planning Dept. | Dist. Assembly |
| 111 | Advocacy programmes and Public forums on permitting and land use planning matters | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  | 5,000.00 |  |  |  |  |  |  |  | X |  |  | Building Inspector ate Unit | Dist. Assembly |
| 112 | Preparation of 2no. local plans and Spatial Development Framework (SDF) | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | X |  |  | Physical Planning Dept. | Dist. Assembly |
| 113 | Enforcement of physical development and Organize periodic development control and monitoring exercise in the district | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  | 10,000.0 0 |  |  |  |  |  |  |  | X |  |  | Building Inspector ate Unit | Dist. Assembly |