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	ASSIN SOUTH DISTRICT ASSEMBLY

	
	2025 ANNUAL ACTION PLAN

	
	OBJECTIVE: To ensure efficient management and administration for effective service delivery. 

	
	PROGRAMME: Management and Administration 

	NO
	PROJECTS 
	LOCATION 
	TIMEFRA
ME (2026) 
	COST 
	PROJECT STATUS 
	IMPLEMENTING INSTITUTION/DEPAR

	
	
	
	Q
1 
	Q
2 
	Q
3 
	Q
4 
	GOG 
	DACF 
	IGF 
	DACFRFG 
	Other 
	Ne w 
	Ongo
ing 
	Lead 
	Collaborating 

	1
	Organization of various statutory meetings (General Assembly, Management, Sub-Committee, 
EXECO, DISEC and others) 
	District Assembly 
	  
	  
	  
	  
	  
	60,000.00 
	  
	  
	  
	  
	X 
	Dist. Asse
	Stakeholders 

	2
	Celebration of National and 
International Days (Emancipation, NAFAC, Independence, etc.) 
	District wide 
	  
	  
	  
	  
	  
	50,000.00 
	  
	  
	20,000.00 
	  
	X 
	Dist. 
Assembl
y 
	MOFA, GES, CNC, etc. 

	3
	Provision of Office and Operational 
Logistics for Effective Service Delivery 
	District wide 
	  
	  
	  
	  
	15,000.00 
	60,000.00 
	  
	  
	  
	  
	X 
	Dist. 
Assembly 
	Procurement Unit 

	4
	Maintain and Manage Assembly Assets and Fleet and Road Safety education
	District wide 
	  
	  
	  
	  
	  
	94,911.36 
	  
	  
	  
	  
	X 
	Dist. 
Assembl 
	Transport Office 

	5
	Provide logistical support to decentralized departments and substructures  
	District wide 
	  
	  
	  
	  
	  
	32,000.00 
	  
	  
	  
	  
	X 
	Dist. 
Assembly 
	Procurement Unit 

	6
	Strengthening Institutional 
Management and Administrative Support 
	District wide 
	  
	  
	  
	  
	  
	289,970.43 
	  
	  
	  
	  
	X 
	Dist. 
Assembl
y 
	Administrative Unit 

	
	OBJECTIVE: To improve effective planning, budgeting, and coordination for sustainable development 

	
	PROGRAMME: Planning, Budgeting and Coordination 

	7
	Preparation of Strategic documents; 
MTDP, Composite budget, FFR, 
AAP, IAP, Annual Accounts, etc. 
	District wide 
	  
	  
	  
	  
	  
	100,000.00 
	  
	  
	  
	  
	X 
	DPCU 
	Dist. Assembly 

	8
	Participatory Monitoring and evaluation of projects and 
programmes 
	District wide 
	  
	  
	  
	  
	  
	70,000.00 
	  
	  
	  
	  
	X 
	DPCU 
	Dist. Assembly 

	9
	Sensitization on Road Safety regulation
	District wide 
	  
	  
	  
	  
	  
	40,000.00 
	  
	  
	  
	  
	X 
	Transport Unit 
	Dist. Assembly 

	10
	Update the District statistical database and district administrative data 
	District wide 
	  
	  
	  
	  
	            1,000.00  
	10,000.00 
	  
	  
	  
	  
	X 
	Statistics Dept. 
	Dist. Assembly 

	11
	Collection of data on businesses in 
2 Area councils and signpost in the District 
	District wide 
Nyankumasi & Andoe 
	  
	  
	  
	  
	            1,500.00  
	  
	  
3,000.0
0  
	  
	  
	  
	X 
	Statistics Dept. 
	Dist. Assembly 

	12
	Contribution to counterpart funding of development projects and programmes 
	District wide 
	  
	  
	  
	  
	  
	20,000.00 
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	Stakeholders 

	
	OBJECTIVE: Deepen political and administrative decentralization  

	
	PROGRAMME: Local Governance and Decentralization  

	13
	Organize DCE’s community engagement and Town Hall Meetings  
	District wide 
	  
	  
	  
	  
	  
	50,000.00 
	  
	  
	  
	  
	X 
	Dist. 
Assembl
y 
	ISD, DPCU 

	
	OBJECTIVE: To strengthen the skills and knowledge of staff and Assembly members 

	
	PROGRAMME: Capacity Building  

	
	HUMAN RESOURCE DEPARTMENT 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	14
	Capacity building and orientation of Staff, NSS personnel and Assembly members (Client service and performance management) 
	District wide 
	  
	  
	  
	  
	  
	30,000.00 
	  
	  
	  
	  
	X 
	HR 
	Consultants 

	
	OBJECTIVE: Improve Quality Education  

	
	PROGRAMME: Education Quality and Access Improvement 

	
	EDUCATION 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	15
	Enhance Educational Support and Performance Improvement 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	x 
	GES 
	Dist. Assembly 

	16
	Procurement of School desks (684 dual, 478 Mono, 110 hexagonal desks) and 200no. Tables & chairs for teachers  
	Selected Schools
	  
	  
	  
	  
	  
	173,763.58 
	  
	  
100,000.
00  
	  
	  
	X 
	Dist. 
Assembl
y 
	GES 

	17
	Organize my first day at school 
	District wide 
	  
	  
	  
	  
	  
	20,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	18
	Capacity building workshop for all basic school teachers and organize refresher course and week celebration for all KG teachers 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	19
	Conduct annual school census in all basic and second cycle schools 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	20
	Sponsorships and bursaries for needy but brilliant students 
	District wide 
	  
	  
	  
	  
	  
	50,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	21
	Support to Ghana School Feeding Programme 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	22
	Orientation workshop for newly posted teachers 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	23
	Organize national standardized assessment test (NSAT) for class 2 & 4 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	GES 
	Dist. Assembly 

	24
	Construction of 1No. 6-Unit Primary Classroom Block with office and store 
	Ongwa
	  
	  
	  
	  
	  
	1,111,970.
23 
	  
	  
	  
	X 
	  
	Dist. 
Assembly 
	GES 

	25
	Construction of 1No. 2-Unit KG Classroom Block with office and store 
	Adiembra,Tebil
	  
	  
	  
	  
	  
	524,111.70 
	  
	  
	  
	X 
	  
	Dist. 
Assembly 
	GES 

	26
	Construction of 1No. 3-Unit Primary Classroom Block with office and store 
	Baafikrom 
	  
	  
	  
	  
	  
	715,244.26 
	  
	  
	  
	X 
	  
	Dist. 
Assembly 
	GES 

	27
	Completion of classroom blocks  
	Ningo, Tutuda, Dadieso 
	  
	  
	  
	  
	  
	2,351,326.
19 
	  
	  
	  
	  
	X 
	Dist. 
Assembl
	GES 

	28
	Completion of 5No. stalled classroom block projects and District Education Office 
	Damtekrom, 
Dawumako 
Ampenkro, 
Tomfokro, Nsuaem, etc.  
	  
	  
	  
	  
	  
	  
	  
	  
	2,000,000.
00 
	  
	X 
	GETFU ND 
	MoE 

	29
	Renovation of classroom blocks 
	District wide 
	  
	  
	  
	  
	  
	200,000.00 
	  
	  
	800,000.00 
	X 
	  
	Dist. 
Assembl
y 
	GES/Donor Partners 

	30
	Construction of Astro turf pitches 
	Amanso and Kruwa
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	MP 
	Dist. Assembly 

	31
	Construction of 1No. 3-unit teachers quarters and community education centre (ICT Centre) 
	Ongwa Area Council 
	  
	  
	  
	  
	  
	  
	  
	  
	2,000,000.
00 
	X 
	  
	MP/MoE
/GIFEC 
	Dist. Assembly 

	32
	Renovate and Operationalize  existing community education centre (ICT Centre) at Nsuaem 
	Nsuaem  
	  
	  
	  
	  
	  
	  
	  
	  
	350,000.00 
	  
	  
	MP/MoE
/GIFEC 
	Dist. Assembly 

	
	OBJECTIVE: Improve access to quality healthcare delivery 

	
	PROGRAMME: Health Service Delivery 

	
	HEALTH 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	33
	Support to Ghana Health Service Activities 
	District wide 
	  
	  
	  
	  
	  
	50,000.00 
	  
	  
	  
	  
	X 
	GHS 
	Dist. Assembly 

	34
	Support to MSHARP, HIV/AIDS activities 
	District wide 
	  
	  
	  
	  
	  
	93,688.18 
	  
	  
	  
	  
	X 
	GHS 
	Dist. Assembly 

	35
	Provision of incentives to staff in deprived areas and sponsorship of at least one hardworking CHO to enrol in midwifery 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	       
20,000.00  
	  
	X 
	GHS 
	Dist. Assembly 

	36
	Support to malaria control programmes and disease control activities  
	District wide 
	  
	  
	  
	  
	  
	20,000.00 
	  
	  
	  
	  
	X 
	GHS 
	Dist. Assembly 

	37
	Completion of 2No. Community based Health and Planning Services (CHPS) and furnishing with CHPS items 
	Appiakrom Dominase 
	  
	  
	  
	  
	  
	 
1,612,225.
54  
	  
	  
	  
	  
	X 
	Dist. 
Assembl
y 
	GHS 

	38
	Completion of 4no. CHPS Compound 
	Assin Kumasi, 
Nkubem 
Framase , Ochiso & Aseratoase 
	  
	  
	  
	  
	     1,671,927.78  
	    
491,180.03  
	 
	  
	     
573,648.00  
	  
	X 
	 
KAKUM 
HIA 
	Dist. Assembly GHS 

	39
	Expansion of  Health Centre  
	Ongwa, Manso 
	  
	  
	  
	  
	  
	  
	  
	  
	     
578,765.45  
	X 
	  
	 
KAKUM 
HIA 
	Dist. Assembly 
GHS 

	40
	Expansion and Renovation of health facilities  
	District wide 
	  
	  
	  
	  
	  
	200,000.00 
	  
	  
	     
250,000.00  
	x 
	  
	Dist. 
Assemby 
	GHS 

	41
	Extension of electricity to CHPS Facilities 
	Bankyease CHPS 
Nuanua Fante CHPS 
	  
	  
	  
	  
	  
	130,000.00 
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	GHS/ECG 

	
	OBJECTIVE: Enhance access to improved and sustainable environmental sanitation services  

	
	PROGRAMME: Water, Environmental Sanitation and Hygiene  

	
	ENVIRONMENTAL HEALTH  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	42
	Evacuate refuse dumps, maintaining and levelling of final disposal site 
	District wide 
	  
	  
	  
	  
	  
	200,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	43
	Organize national sanitation day 
	District wide 
	  
	  
	  
	  
	  
	120,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	44
	Undertake district wide fumigation exercise  
	District wide 
	  
	  
	  
	  
	  
	160,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	45
	Monitor and supervise environmental service providers 
	District wide 
	  
	  
	  
	  
	  
	50,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	46
	Conduct sensitization on WASH activities 
	District wide 
	  
	  
	  
	  
	  
	20,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	47
	Support implementation of community led total sanitation 
	District wide 
	  
	  
	  
	  
	  
	40,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	48
	Undertake desilting of public drains and gutters 
	District wide 
	  
	  
	  
	  
	  
	30,000.00 
	  
	  
	  
	  
	X 
	EHSU NADMO 
	Dist. Assembly 

	49
	Sensitization and training on school health hygiene for students, teachers and cooks in basic schools  
	District wide 
	  
	  
	  
	  
	  
	30,000.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	50
	Conduct domicilary premises, hospitality premises and house inspection to ascertain the level of sanitation 
	District wide 
	  
	  
	  
	  
	  
	787,205.00 
	  
	  
	  
	  
	X 
	EHSU 
	Dist. Assembly 

	51
	Provision of two slaughter facilities 
(house) in Assin Andoe and 
Nyankomase  Ahenkro Markets 
	Andoe 
Nyankumasi market 
	  
	  
	  
	  
	  
	  
	  
	 
	  
1,000,000.
00  
	X 
	  
	Dist. 
Assembl
y 
	EHSU/Agric  

	
	WATER 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	52
	Drilling and Construction of 5No. 
Mechanized Boreholes with Overhand tanks 
	Nkwanta, Domi and Others
	  
	  
	  
	  
	  
	1,200,000.
00 
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	EHSU 

	53
	Drilling and Construction of 5No. 
Handpumps  
	Selected Schools
	  
	  
	  
	  
	  
	473,763.58 
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	EHSU 

	54
	Repair and maintenance of 10 No. Boreholes 
	District wide 
	  
	  
	  
	  
	  
	200,000.00 
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	EHSU 

	55
	Rehabilitate and operationalize the Adankwaman water project through 
household connection for consumption 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	  
1,000,000.
00  
	x 
	  
	CWSA 
	Dist. Assembly 

	
	OBJECTIVE: To strengthen disaster preparedness and risk reduction 

	
	PROGRAMME: Disaster Management and Prevention 

	
	NADMO 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	56
	Public sensitization on disaster prevention and mitigation 
	  District wide
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	X 
	NADMO 
	Dist. Assembly 

	57
	Procure relief items for disaster victims 
	District wide 
	  
	  
	  
	  
	  
	100,000.00 
	  
	  
	  
	  
	X 
	NADMO 
	Dist. Assembly 

	58
	Prepare disaster preparedness, risk and heat plans 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	NADMO 
	Dist. Assembly 

	59
	Undertake emergency response 
	District wide 
	  
	  
	  
	  
	  
	10,000.00 
	  
	  
	  
	  
	X 
	NADMO 
	Dist. Assembly 

	
	OBJECTIVE: Mitigate climate change impacts and enhance resilience 

	
	PROGRAMME: Climate Change and Green Economy 

	
	Climate Change Activities 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	60
	Conduct Climate Change awareness and sensitization  programmes in line with the GCFRP 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
15,000.00  
	  
	X 
	DPCU 
	Dist. Assembly 

	61
	Conduct Fire Education in all 10 
CREMAs 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
40,000.00  
	  
	X 
	DPCU 
	Dist. Assembly 

	62
	Conduct Forest Monitoring to ensure compliance with REDD+ Strategy 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
18,000.00  
	  
	X 
	DPCU 
	Dist. Assembly 

	63
	Undertake national tree for life planting exercise 
	District wide 
	  
	  
	  
	  
	  
	        
5,000.00  
	  
	  
	         
5,000.00  
	  
	X 
	NADMO 
	Dist. Assembly 

	
	OBJECTIVE: Strengthen social protection for the vulnerable and excluded  

	
	PROGRAMME: Social Protection and Poverty Reduction  

	
	Social Welfare 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	64
	Supervision and Impact Assessment of LEAP Payments to Households and Case Management 
	66 LEAP communities 
	  
	  
	  
	  
	            2,000.00  
	3,000.00 
	      
1,000.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	65
	Capacity building and Skills training for 80 PWDs 
	District wide 
	  
	  
	  
	  
	            3,000.00  
	3,000.00 
	      
4,000.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	66
	Distribution of Modalities aids to 
200 PWDs 
	District wide 
	  
	  
	  
	  
	            3,000.00  
	4,000.00 
	      
1,600.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	67
	Conduct Social Investigations & enquiries 
	District wide 
	  
	  
	  
	  
	            1,000.00  
	1,000.00 
	         
600.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	68
	Monitoring and Registration of 
Day-Care Centres (ECDC), NGOs 
& ECDC Care givers & 
Supervisrors training 
	District wide 
	  
	  
	  
	  
	            2,000.00  
	1,000.00 
	      
1,500.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	69
	NHIS Indigene Registration and Renewal for 1000 No. vulnerable persons 
	District wide 
	  
	  
	  
	  
	            4,000.00  
	8,000.00 
	      
1,000.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	70
	After care services, Case management, follow-ups, family tracing & SWIMS Reporting 
	District wide 
	  
	  
	  
	  
	            3,000.00  
	1,000.00 
	      
1,000.00  
	  
	  
	  
	X 
	DSW 
	Dist. Assembly 

	
	Integrated Social Services (ISS) Implementation 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	71
	Sensitization on Gender Based 
Violence Prevention & Response in 10 schools & 5 communities 
	Specific communities & schools 
	  
	  
	  
	  
	            3,000.00  
	        
3,000.00  
	      
1,000.00  
	  
	         
5,000.00  
	  
	X 
	DSW 
	Dist. Assembly 

	72
	Social Education on Social Issues in 10 No. schools & communities 
	District wide 
	  
	  
	  
	  
	            2,500.00  
	        
3,000.00  
	      
2,000.00  
	  
	         
4,000.00  
	  
	X 
	DSW 
	Dist. Assembly 

	73
	ISS Stakeholder Review Meetings, Strengthening Referrals & Linkages 
	District wide 
	  
	  
	  
	  
	            1,000.00  
	        
1,000.00  
	      
2,000.00  
	  
	         
2,000.00  
	  
	X 
	DSW 
	Dist. Assembly 

	
	Child Labour Activities 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	74
	Sensitisation of 20 communities on Child Labour, Forced Labour using behavioural change techniques 
	Specific communities 
	  
	  
	  
	  
	  
	        
2,000.00  
	      
4,000.00  
	  
	       
30,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	75
	Undertake Continuous training of 
District Child Protection Committee members to better coordinate child labor related interventions  
	Dist. Assembly Conference room 
	  
	  
	  
	  
	  
	        
2,000.00  
	      
2,000.00  
	  
	         
3,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	76
	Train members of the Social Services Sub-Committee to support coordination and implementation of 
child labor activities in 
communities 
	Dist. Assembly Conference room 
	  
	  
	  
	  
	  
	        
2,000.00  
	      
2,000.00  
	  
	         
3,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	77
	Training of 100 CCPC members on 
Child protection related issues  
	Dist. Wide 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	10,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	78
	Monthly Radio sensitization on child protection in the District 
	Nyankumasi Ahenkro (Bohyeba fm) 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
1,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	79
	Training of 10 SISOs on Child labour related activities 
	10 Circuits 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
2,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	80
	Support 10 School Management 
Committees (SMCs) and PTAs to monitor and report child labor acts  
	Specific schools 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
2,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	81
	Establish child protection clubs in 5 schools as structures for advocacy   
	Specific schools 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
5,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	82
	Organize training for 
HODs/Management to provide conscious support to social services  
	Dist. Assembly Conference room 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
2,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	83
	Provide comprehensive child protection remediation support including psychosocial counselling 
	DSW office  
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
1,000.00  
	  
	X 
	DCPC 
	Dist. Assembly 

	84
	Ensure vulnerable populations benefit from various social protection services and safety net programmes
	Dist. Wide 
	  
	  
	  
	  
	  
	        
2,000.00  
	  
	  
	         
1,000.00  
	X 
	  
	DCPC 
	Dist. Assembly 

	
	 Community Development 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	85
	Support to Gender mainstreaming activities & VSLAs 
	Dist. Wide 
	  
	  
	  
	  
	2,000.00 
	        
2,000.00  
	1,000.0
0 
	  
	4,000.00 
	  
	X 
	Gender 
Desk 
Office 
	Dist. Assembly 

	86
	Increase Participation of women in governance and decision making at the local level through orientation and training 
	Dist. Wide 
	  
	  
	  
	  
	  
	        
2,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Gender 
Desk 
Office 
	Dist. Assembly 

	87
	Extension services, vocational training & self-help initiatives 
	Dist. Wide 
	  
	  
	  
	  
	2,000.00 
	        
2,000.00  
	1,200.00 
	  
	  
	  
	X 
	Gender 
Desk 
Office 
	Dist. Assembly 

	
	OBJECTIVE: Promote local economic development through agriculture and job creation 

	
	PROGRAMME: Agriculture & Local Economic Development (LED) 

	88
	Technical Training of 25  Apprentices in Welding, Fabrication and Mechanical  Engineering to promote local economic development (LED) 
	District wide 
	  
	  
	  
	  
	  
	    
5,000.00  
	  
	  
	     
5,000.00  
	  
	X 
	RTF 
	Dist. Assembly 

	89
	Apprenticeship to entrepreneurship training for 150 youth and 50PWDs 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
10,000.00  
	  
	X 
	BAC 
	Dist. Assembly 

	90
	Agric and Agribusiness to entrepreneurship training for 200 youth and 50 PWDs 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
10,000.00  
	  
	X 
	BAC 
	Dist. Assembly 

	91
	MSME business acceleration training for 50 women owned 
businesses 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	     
5,000.00  
	  
	X 
	BAC 
	Dist. Assembly 

	92
	Business Counseling to promote 
Local economic development (LED) 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	       
10,000.00  
	  
	X 
	BAC 
	Dist. Assembly 

	93
	Support Graduate Apprentice to acquire NVTI certificates 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	         
5,000.00  
	  
	X 
	RTF 
	BAC 

	94
	Promotion of tourism development across the District and participation in Exhibitions  
	District wide 
	  
	  
	  
	  
	  
	    
5,000.00  
	  
	  
	  
	  
	X 
	DPCU 
	Dist. Assembly 

	95
	Collect and build database for development  of tourist sites in the District 
	District wide 
	  
	  
	  
	  
	  
	    
5,000.00  
	  
	  
	  
	  
	X 
	DPCU 
	Dist. Assembly 

	96
	Operationalize the factory under 1D1F Progarmme 
	Kyekyewere 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	X 
	  
	Dist. 
Assembl
y 
	REP, MoTA 

	
	OBJECTIVE: Enhance agricultural production and agri-business for economic transformation  

	
	PROGRAMME: Agricultural and Agribusiness Development  

	
	AGRICULTURE 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	97
	Enhance the adoption of improved technologies by small holder farmers and other organizations to 
increase yields of crops under Feed Ghana Programme 
	District wide 
	  
	  
	  
	  
	  
	  
61,840.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	98
	Improve livestock technologies to increase production of local poultry birds by 10% and small ruminants and pigs by 15% under Feed Ghana Programme 
	District wide 
	  
	  
	  
	  
	  
	    
6,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	99
	Reduce post-harvest losses along maize, rice and cassava by 15%, 20% and 30% respectively by 2026 
	District wide 
	  
	  
	  
	  
	  
	    
6,400.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	100
	Improve adoption of improved technologies by men and women farmers by 25% by 2026 
	District wide 
	  
	  
	  
	  
	  
	  
26,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	101
	Increase income from livestock rearing by men and women by 10% and 25% respectively by 2026 
	District wide 
	  
	  
	  
	  
	  
	  
10,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	102
	Develop 100 micro and 15 small scale irrigation schemes as well as agricultural management systems 
	District wide 
	  
	  
	  
	  
	  
	    
2,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	103
	Reduce stunting and overweight in children as well as Vit. A, iron and iodine deficiencies in children and women of reproductive age by 20% 
	District wide 
	  
	  
	  
	  
	  
	    
3,000.00  
	      
1,000.00  
	  
	  
	  
	X 
	Dept of Agric 
	Dist. Assembly 

	
	OBJECTIVE: To create sustainable jobs for Ghanaians.  

	
	PROGRAMME: 24 Hour Economy Market & Accelerated Export Development 

	104
	Construction of Model Market 
Complex with Ancillary Facilities 
	  
	  
	  
	  
	  
	  
	4,684,408.
96 
	  
	  
	  
	  
	  
	MoLGC
RA 
	Dist. Assembly 

	
	OBJECTIVE: Expand infrastructure development for socio-economic growth 

	
	PROGRAMME:  Infrastructure & Basic Services 

	105
	Construction of 10 No.  Pipe culverts and Bridges 
	District wide 
	  
	  
	  
	  
	  
	    
200,000.00  
	  
	  
300,000.
00  
	  
	X 
	  
	Works Dept. 
	Dist. Assembly 

	106
	 Rehabilitation and Spot improvement of 40km of District feeder roads  
	District wide 
	  
	  
	  
	  
	  
	    
300,000.00  
	  
	  
	  
	X 
	  
	Works Dept. 
	Dist. Assembly 

	107
	Enhance and expand rural telecommunication infrastructure and network coverage. 
	District wide 
	  
	  
	  
	  
	  
	  
	  
	  
	 1,000,000.
00  
	x 
	  
	GIFEC/T ELCOS 
	Dist. Assembly 

	108
	Rural Electrification Extension Project 
	District wide 
	  
	  
	  
	  
	  
	 1,000,000.
00  
	  
	  
	  1,000,000.
00  
	x 
	  
	ECG, MoEGT 
	Dist. Assembly 

	
	OBJECTIVE: Promote sustainable spatially integrated development of human settlements 

	
	PROGRAMME:  Spatial Planning & Human Settlement Development 

	
	PHYSICAL PLANNING 
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  
	  

	109
	Street naming and property numbering  
	District wide 
	  
	  
	  
	  
	  
	      
20,000.00  
	  
	  
	  
	X 
	 
	Physical Planning Dept. 
	Dist. Assembly 

	110
	Preparation of 2 No. New spatial plans 
	District wide 
	  
	  
	  
	  
	  
	      
10,000.00  
	  
	  
	  
	  
	X 
	Physical Planning Dept. 
	Dist. Assembly 

	111
	Advocacy programmes and Public forums on permitting and  land use planning matters  
	District wide 
	  
	  
	  
	  
	  
	      
10,000.00  
	      
5,000.00  
	  
	  
	  
	X 
	Building Inspector ate Unit 
	Dist. Assembly 

	112
	Preparation of 2no. local plans and 
Spatial Development 
Framework (SDF) 
	District wide 
	  
	  
	  
	  
	  
	      
10,000.00  
	  
	  
	  
	  
	X 
	Physical Planning Dept. 
	Dist. Assembly 

	113
	Enforcement of physical development and Organize periodic development control and monitoring exercise in the district 
	District wide 
	  
	  
	  
	  
	  
	      
10,000.00  
	    
10,000.0
0  
	  
	  
	  
	X 
	Building Inspector ate Unit 
	Dist. Assembly 
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0332098227
Your Ref: HA 101/134/01 215t December, 2023
R A T S

RE: REQUEST FOR REVISION OF DPAT VI (2021) WORK PLANS AND BUDGETS
With reference to your letter dated 18™ December, 2023 requesting for revised work plans and
budget of DPAT VI, we submit herewith, the work plan and budget of Assin South District
Assembly for your perusal and necessary action.

Thank you.

ol

RICHARD ANSAH AMOAFO
(DISTRICT COORDINATING DIRECTOR)
For: DISTRICT CHIEF EXECUTIVE

THE MINISTER

MINISTRY OF LOCAL GOVERNMENT,
DECENTRALISATION AND RURAL DEVELOPMENT
ACCRA.

THRO’

THE REGIONAL MINISTER

REGIONAL COORDINATING COUNCIL
CENTRAL REGION

CAPE COAST.

Attn:
THE REGIONAL ECONOMIC PLANNING OFFICER




